## Weekly Report
	Weekly Report – 31;4 SEPT

Task	Implemented	Description	Notes
transaction_e current_transaction	Yes	A typedef enum data type was created for function tasks to manage the current transaction that is taking place in the verification environment	typedef enum {READ_TRANSACTION, WRITE_TRANSACTION} transaction _e
the management of the current transaction	Yes	The functions of the generator, driver and monitor classes have received different instructions depending on the current transaction
read transaction	Yes	instructions for generating and verifying a read transaction
mailbox check	Yes	check the mailbox for messages that have not been removed
DUT debuging	almost	I brought certain DUT bugs to the designer’s attention	protocol errors and delays
error counter	yes	counter for scoreboard detected errors

## Verification Plan
				Verification Plan for Next Week

Task	Time
verification of several consecutive transactions in the same testcase	1-2 days
coverage class	1 day
test cases	2 day
code review	1 day